## Progress
Date | Highlights | Details | Next Steps
2019-02-25 | Started interfacing pulse oximeter sensors available in the lab | Using Arduino UNO and MAX3501 Pulse Oximeter | Develop Arduino program for sensor control and data acquisition and transfer
Started sketching sensor holder prototype:
|  | Forehead design | 3D Design and printing of designs
Neck design
| Started building the data gathering, communication central | Python script, uses MQTT | Develop Python program for data transfer and logging
Order parts as listed in proposal
2019-03-26 | Continued interfacing pulse oximeter sensors available in the lab | Using Arduino UNO and MAX3501 Pulse Oximeter | Sensor does not seem to be performing as desired/expected
|  | Using the PulseSensor from World Famous Electronics | Sensor performs on the Arduino, now adapting to the ESP32
| Tested heart rate sensor for forehead, neck and earlobe | PulseSensor performs in every scenario | Build fixtures
| Started design of three fixture models | Modelus are specific to forehead, neck, and earlobe | Will print models and test fixing to sensors, components